Case Study on the Preparation of a Software Project Plan Covering Scope, Timeline, and Team Roles for a Sample Application

Aim

To prepare a structured software project plan defining the scope, timeline, responsibilities, resources, and deliverables for a sample software application.

Objective

Define the project scope and major requirements.

Divide the work into manageable tasks and milestones.

Assign team roles and responsibilities.

Estimate the project timeline, resources, risks, and deliverables.

Selected Software Application

Online Food Delivery System

Overview

The Online Food Delivery System enables customers to discover restaurants, browse menus, place orders, make online payments, and track deliveries. Restaurants manage menus and orders, delivery partners handle delivery updates, and administrators monitor the platform.

Project Scope

In Scope

Customer registration and login.

Restaurant and menu listing with search.

Cart management and order placement.

Payment status handling through a payment gateway test/sandbox environment.

Restaurant order acceptance and status updates.

Basic delivery status tracking.

Admin management and summary reports.

Out of Scope

Building a physical delivery fleet.

Developing a new payment network.

Advanced AI-based restaurant recommendations.

International multi-currency operations.

Project Requirements

| Requirement Type | Description |
| --- | --- |
| Functional | Registration/login, restaurant search, menu viewing, cart, order placement, payment status, order updates, delivery tracking, admin reports |
| Non-functional | Usable interface, secure authentication, reasonable response time, reliable data storage, maintainable design, access control |
| Assumptions | Internet connectivity is available; payment gateway sandbox and map/test services can be used; project uses sample data |
| Constraints | Fixed academic deadline, limited student team, no production financial transactions, and limited test devices |

Work Breakdown Structure (WBS)

| WBS ID | Task | Deliverable |
| --- | --- | --- |
| 1.0 | Project initiation and requirement gathering | Project brief and requirement list |
| 2.0 | Scope and project planning | Scope statement, schedule, risk register |
| 3.0 | UI and system design | Wireframes, database design, architecture sketch |
| 4.0 | Customer and restaurant modules | Registration, menu, cart, order screens |
| 5.0 | Payment and delivery workflow | Sandbox payment flow and delivery status |
| 6.0 | Admin module | Basic management and reports |
| 7.0 | Testing and defect fixing | Test cases and test report |
| 8.0 | Deployment and documentation | Demo deployment, user guide, final report |

Project Timeline

| Week | Planned Activities | Milestone / Output |
| --- | --- | --- |
| 1 | Gather requirements; identify users and use cases | Approved project brief and requirements |
| 2 | Define scope, risks, and database/UI design | Scope baseline and design draft |
| 3–4 | Develop registration, restaurant listing, and menu | Core browsing modules |
| 5 | Develop cart and order placement | Order workflow completed |
| 6 | Integrate payment sandbox and order status updates | Payment and restaurant workflow demo |
| 7 | Build basic delivery tracking and admin reports | End-to-end feature-complete build |
| 8 | Testing, corrections, deployment, and documentation | Final demonstration and submission |

Team Roles and Responsibilities

| Role | Responsibilities | Main Deliverables |
| --- | --- | --- |
| Project Manager / Analyst | Plan tasks, track progress, gather requirements, manage risks | Project plan, meeting notes, status report |
| UI/UX Designer | Design user journeys, page layouts, and navigation | Wireframes and screen designs |
| Frontend Developer | Implement customer and restaurant-facing screens | Working user interface |
| Backend Developer | Implement APIs, business logic, authentication, and order handling | Backend services and API documentation |
| Database / Integration Engineer | Design data structure and integrate sandbox payment/map services | Database schema and integration tests |
| QA Tester | Prepare test cases, execute tests, report defects, retest fixes | Test plan and test report |

Milestones and Monitoring

End of Week 1: requirements reviewed.

End of Week 2: scope and design baseline agreed.

End of Week 5: core ordering workflow demonstrated.

End of Week 7: feature-complete build available for testing.

End of Week 8: final testing, documentation, and presentation completed.

Review progress weekly and record completed tasks, blockers, defects, and schedule changes.

Risk Analysis

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Requirements change late | Schedule delay and rework | Confirm scope early; record and prioritize change requests |
| Payment integration fails | Checkout cannot be demonstrated | Use sandbox mode and prepare a simulated payment fallback |
| Data loss or incorrect orders | Unreliable demonstration | Validate inputs, back up test data, and test order state transitions |
| Team member unavailable | Tasks delayed | Document work, share knowledge, and assign a backup owner |
| Insufficient testing time | Defects remain unnoticed | Reserve Week 8 for testing and avoid adding features near submission |

Testing and Acceptance Criteria

| Test Area | Acceptance Criteria |
| --- | --- |
| Registration/login | Valid users can sign in; invalid credentials are rejected |
| Search and menu | Users can find restaurants and view available menu items |
| Cart and order | Selected items and totals are correct; order is saved once |
| Payment status | Sandbox success/failure outcomes are reflected correctly |
| Order tracking | Order status progresses through defined stages |
| Admin reports | Authorized administrator can view basic order summaries |

Results

The project scope separates essential functions from optional enhancements.

The eight-week schedule provides milestones for design, development, integration, testing, and delivery.

Defined team roles make ownership and expected outputs clear.

Risk planning and acceptance criteria help control delays and verify that the application meets its objectives.

Conclusion

A software project plan provides a practical baseline for delivering an Online Food Delivery System within a defined academic schedule. Clear scope, a work breakdown structure, an eight-week timeline, assigned responsibilities, risk controls, and testable acceptance criteria help the team coordinate its work and measure completion. The plan should be reviewed regularly so that changes are assessed without compromising essential features or final testing.